## Instructions
FedRAMP® Continuous Monitoring Deliverables Template
How to Contact Us
Questions about FedRAMP or this document should be directed to info@fedramp.gov. For more information about FedRAMP, visit the website at https://www.fedramp.gov.
About This Template and Who Should Use It
This template uses the term authorizing official (AO) to refer to each leveraging Agency’s AO. This template summarizes what continuous monitoring (ConMon) deliverables must be submitted to the Cloud Service Offering (CSO) designated document repository for the AO's review. Cloud Service Providers (CSPs) must use this worksheet to document the schedule and location of CSO ConMon deliverables. Initial submission -CSPs in the continuous monitoring phase: Submit this completed worksheet as soon as possible (within a reasonable timeframe) and coordinate with your AO on the schedule for the initial submission. -CSPs pending authorization - Complete this worksheet within 10 business days from receipt of the authorization. Maintaining this worksheet -Coordinate with your AO(s) on any updates that are needed after the initial submission. -Update the worksheet when deliverables are completed and annually, by the CSO's Annual Assessment due date. Where to post this worksheet -For CSPs using Connect.gov: Post the completed worksheet in the top-level Continuous Monitoring directory. Coordinate with your POCs to ensure the document is posted to the customer-facing Continuous Monitoring directory (if applicable). -For CSPs that do not use Connect.gov and maintain their own document repository: Post the completed worksheet in the top-level customer-facing Continuous Monitoring directory.

## Con Mon Deliverables
FedRAMP Continuous Monitoring Deliverables Template
CSP: | (Cloud Service Provider name) | CSO: | (Cloud Service Offering name)
Impact Level: | (select) | Service Model: | (select) | Deployment Model: | (select)
FedRAMP Authorized Date: | MM/DD/YYYY | Last Annual Assessment: | MM/DD/YYYY | Completed by: | (main POC name)
Location of Deliverables (Link/Path)
Activity | Control ID | Description | Frequency | Delivery Dates | FedRAMP Internal (if applicable) | Connect.gov users: Work with your POCs to identify the location | Responsible?
Continuous Monitoring Monthly Executive Summary | CA-05, RA-05a | An executive summary of the monthly continuous monitoring (ConMon) submission that includes the most current Plan Of Actions and Milestones (POA&M), submitted to the AO via the designated repository. | Monthly |  |  |  | CSP
Collaborative Continuous Monitoring | CA-07g | CSOs with more than one (1) agency ATO must implement a collaborative ConMon approach as described in the FedRAMP Collaborative ConMon Quick Guide, a guide for Multi-Agency Continuous Monitoring. This requirement applies to all FedRAMP-authorized CSOs, as each agency customer is responsible for performing ConMon oversight. | CSP defined, in accordance with the FedRAMP Collaborative ConMon Quick Guide (https://www.fedramp.gov/documents-templates/) |  |  |  | CSP
Vulnerability and Configuration Scanning | RA-05a, CA-07, CM-06 | Operating System (OS)/infrastructure, web application, database, container and configuration scans submitted to the AO via the designated repository. | Monthly |  |  |  | CSP
Plan of Action & Milestones (POA&M) | CA-05 | Updated as needed and submitted to the AO via the designated repository. | Monthly |  |  |  | CSP
Inventory | CM-08 | Updated as needed and submitted to the AO via the designated repository. | Monthly |  |  |  | CSP
Contingency Plan Test Plan | CP-04a | Documented plan to perform a test and exercise of the IT Contingency Plan; the plan is submitted to the AO via the designated repository. | Moderate and High - Functional, at least annually Low - Classroom exercise/table top written test, at least every 3 years Li-SaaS - N/A |  |  |  | CSP
Contingency Plan Test Results | CP-04a | Perform contingency plan testing; the results are inserted into Appendix F of the IT Contingency Plan and submitted to the AO via the designated repository. Test date, results, and participants must be noted in the SSP. | Moderate and High - Functional, at least annually Low - Classroom exercise/table top written test, at least every 3 years Li-SaaS - N/A |  |  |  | CSP
Incident Response Test Plan | IR-03 | Documented plan to perform incident response testing is submitted to the AO via the designated repository. | Moderate - Functional, at least annually High - At least every six (6) months, including functional at least annually Low and Li-SaaS - N/A |  |  |  | CSP
Incident Response Test Results | IR-03 | Perform incident response testing and submit to the AO via the designated repository. | Moderate - Functional, at least annually High - At least every six (6) months, including functional at least annually Low and Li-SaaS - N/A |  |  |  | CSP
System Security Plan (SSP) and Supporting Documents Update | PL-02c, PL-02d | Update the SSP and supporting documents, and submit to the 3PAO at least thirty (30) days prior to the initiation of annual assessment activities. | Annually |  |  |  | CSP
Static Code Analysis Methodology | SA-11 (01) | The service provider must document its methodology for reviewing newly developed code for the service in its ConMon plan. As with all SSP supporting documents, the ConMon plan must be submitted to the 3PAO at least thirty (30) days prior to the initiation of annual assessment activities. | Moderate and High - Annually Low and Li-SaaS - N/A |  |  |  | CSP
Security Assessments Plan (SAP) | CA-02 | Plan for the annual assessment developed by the 3PAO and submitted to the AO via the designated repository. | Annually |  |  |  | 3PAO
Penetration Testing performed by Independent Assessor (High and Moderate) | CA-08, CA-08 (01) | Penetration test. For High and Moderate systems, penetration testing is conducted by the 3PAO and included in/with the SAR. Submit to the AO via the designated repository. | Annually |  |  |  | 3PAO
Penetration Testing (Low and Li-SaaS) | CA-08 | Penetration test. Submit the report to the AO via the designated repository. | Annually |  |  |  | CSP
Penetration Testing - Red Team Test Plan | CA-08 (02) | Documented plan to perform red team exercises. Submit the report to the AO via the designated repository. | Moderate and High - Annually Low and Li-SaaS - N/A |  |  |  | CSP
Penetration Testing - Red Team Test Report | CA-08 (02) | Perform red team exercises and document the results. Submit the report to the AO via the designated repository. | Moderate and High - Annually Low and Li-SaaS - N/A |  |  |  | CSP
Vulnerability and Configuration Scanning | RA-05a, CA-07, CM-06 | Scan of OS/infrastructure, web applications, containers, databases, and configurations conducted directly by the 3PAO or with 3PAO oversight and submitted in/with SAR. | Annually |  |  |  | 3PAO
Security Assessments and Security Assessment Report (SAR) | CA-02c | Security assessment, including any specialized assessments, conducted by the 3PAO. Submit the report to the AO via the designated repository. | Annually |  |  |  | 3PAO
Security Alerts, Advisories, and Directives | SI-05 | Service Providers must address the CISA Emergency and Binding Operational Directives applicable to their cloud service offering per FedRAMP guidance. This includes listing the applicable directives and stating compliance status. | Ad hoc (in accordance with FedRAMP guidance) | Ad hoc (in accordance with FedRAMP guidance) |  |  | CSP

## Record of Change
Record of Changes for Template
Date | Description | Version | Author
2024-02-15 | Initial publication | 1 | FedRAMP
2024-03-04 | Added Instructions tab - Corrected issues with Service Model dropdown - Updated Frequency for "Collaborative Continuous Monitoring (applicable to Agency Authorized CSPs only)" - Updates to clarify Low and Li-SaaS requirements - Integrated CA-07 and CM-06 for configuration scanning. Updated both instances of "Vulnerability Scanning" to "Vulnerability and Configuration Scanning" - Updated "Location of Deliverables" into two columns for specifying JAB-Internal and Customer-Facing locations. - Formatting updates - Added Security Alerts, Advisories, and Directives SI-05 | 2 | FedRAMP
2024-10-08 | Updated to align with OMB Memo M-24-15 and remove JAB and PMO references | 3 | FedRAMP
2024-12-04 | Updated minor formatting | 3.1 | FedRAMP